## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US101 | As an ML developer, I want to implement email text cleaning using regex, stopwords, and lemmatization so that raw emails become suitable for machine learning. | MUST HAVE |  | ML Developer | Completed
Sprint 1 | Sprint 1 | US102 | As a data engineer, I want to combine email subject and body into a single cleaned text field so that the complete email context is available for classification. | MUST HAVE | US101 | ML Developer | Completed
Sprint 1 | Sprint 1 | US103 | As a data scientist, I want to create a pandas DataFrame with cleaned emails and category labels so that data is structured for model training. | MUST HAVE | US102 | Data Scientist | Completed
Sprint 2 | Sprint 2 | US104 | As an ML engineer, I want to apply TF-IDF vectorization to cleaned email texts so that text data becomes numerical features for classifiers. | MUST HAVE | US103 | ML Engineer | Completed
Sprint 2 | Sprint 2 | US105 | As an ML developer, I want to train Logistic Regression model on TF-IDF features so that emails can be categorized into complaint, request, feedback, spam. | MUST HAVE | US104 | ML Engineer | Completed
Sprint 2 | Sprint 2 | US106 | As a data scientist, I want to evaluate model performance with train/test split and classification metrics so that I can validate the classifier accuracy. | MUST HAVE | US105 | Data Scientist | Completed
Sprint 3 | Sprint 3 | US107 | As an ML engineer, I want to extract urgency keywords like 'urgent', 'ASAP', 'not working' from emails so that high priority emails can be identified quickly. | MUST HAVE | US106 | ML Engineer | Completed
Sprint 3 | Sprint 3 | US108 | As an AI developer, I want to train a classifier to predict urgency levels (high/medium/low) using TF-IDF features so that emails are prioritized for response. | MUST HAVE | US107 | AI Engineer | Completed
Sprint 3 | Sprint 3 | US109 | As a data scientist, I want to combine rule-based urgency detection with ML predictions so that accuracy is improved for critical customer issues. | MUST HAVE | US108 | Data Scientist | Completed
Sprint 4 |  | US110 | As a support manager, I want a dashboard showing email counts by category and urgency so that team workload can be monitored. | SHOULD HAVE | US106 | support manager | not started

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 58 | 3 | 4 | 2 | 4 | 4 | 1 | 8 | 0 | 4 | 8 | 8 | 7 | 3 | 2
SPRINT 1 BACKLOG
US101 | T-1 | Implemented email text cleaning pipeline using regex (remove emails/URLs), punctuation removal, stopwords filtering, and lemmatization; validated on sample emails. | 2025-11-27 | 2025-11-30 | ML Developer | Preprocessing | 3- Completed | 8 | Day 1: 2; Day 2: 2; Day 4: 2; Day 7: 2
US102 | T-2 | Merged subject + body into a single cleaned_text field and ensured consistent formatting for downstream classification. | 2025-12-01 | 2025-12-05 | Data Engineer | Feature Prep | 3- Completed | 6 | Day 9: 1; Day 10: 2; Day 11: 2; Day 12: 1
US103 | T-3 | Created pandas DataFrame with subject, body, cleaned_text, and label columns; exported cleaned dataset for model training. | 2025-12-06 | 2025-12-11 | Data Scientist | Feature Prep | 3- Completed | 6 | Day 4: 2; Day 5: 2; Day 7: 2
US104 | T-4 | Applied TF‑IDF vectorization on cleaned_text column and generated feature matrix for baseline classifiers. | 2025-12-12 | 2025-12-15 | ML Engineer | Feature Prep | 3- Completed | 6 | Day 3: 1; Day 5: 2; Day 6: 1; Day 11: 1; Day 12: 1
US105 | T-5 | Trained Logistic Regression baseline model on TF‑IDF features for category classification (complaint/request/feedback/spam). | 2025-12-16 | 2025-12-19 | ML Engineer | Model Training | 3- Completed | 10 | Day 7: 4; Day 9: 3; Day 10: 2; Day 11: 1
US106 | T-6 | erformed train/test split and evaluated model using accuracy and classification metrics (precision/recall/F1). | 2025-12-20 | 2025-12-25 | Data Scientist | Evaluation | 3- Completed | 6 | Day 10: 2; Day 11: 2; Day 12: 2
US107 | T-7 | Implemented rule-based urgency detection by extracting urgency keywords (urgent, ASAP, not working) to flag high priority emails. | 2025-12-26 | 2025-12-28 | ML Engineer | Urgency Rules | 3- Completed | 4 | Day 1: 1; Day 2: 2; Day 3: 1
US108 | T-8 | uilt ML-based urgency prediction pipeline (high/medium/low) using TF‑IDF features and prepared training/testing setup for urgency model. | 2025-12-29 | 2026-01-04 | AI Engineer | Urgency ML | 3- Completed | 8 | Day 12: 3; Day 13: 3; Day 14: 2
US109 | T-9 | Designed hybrid urgency decision logic combining rule-based signals with ML urgency predictions to improve prioritization. | 2026-01-05 | 2026-01-08 | AI Engineer | Hybrid Logic | 3- Completed | 4 | Day 10: 2; Day 11: 2

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Dataset column mismatch (subject/body not consistent across datasets). | Inspected dataset schema, selected required columns, and standardized naming (subject, body).
Sprint 1 | Day 2 | Noisy text (URLs, email IDs, punctuation) affecting preprocessing quality. | Added regex rules to remove emails/URLs and punctuation cleanup in cleaning function.
Sprint 1 | Day 3 | NLTK stopwords/WordNet lemmatizer errors (missing resources). | Downloaded required NLTK resources and validated stopword removal + lemmatization pipeline.
Sprint 1 | Day 4 | Cleaned text not matching expected output for some sample emails. | Tested cleaning on sample emails and tuned preprocessing order (lowercase → regex → punctuation → stopwords → lemmatize).
Sprint 2 | Day 1 | Model training took a lot of time | Adjusted model/training settings
Sprint 2 | Day 2 | Train/test split and label alignment issues. | Used train_test_split with fixed random_state and verified X/y shapes before training.
Sprint 2 | Day 3 | Baseline accuracy not stable due to preprocessing variations. | Kept a single consistent cleaning + TF‑IDF pipeline, re-trained Logistic Regression and compared results.
Sprint 2 | Day 4 | Need correct evaluation metrics for multi-class model. | Evaluated using accuracy + classification metrics (precision/recall/F1) and saved results for reporting.
Sprint 2
Sprint 3
Sprint 3
Sprint 3
Sprint 3
Sprint 3

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-27 | 2025-12-11 | Data Engineer | Automate cleaning scripts | Manual cleaning steps | Using regex-based preprocessing | Standardized preprocessing pipeline
2 | Sprint 2 | 2025-12-12 | 2025-12-25 | ML Engineer | Hyperparameter tuning | Training without evaluation | Baseline + transformer comparison | Selected best-performing models
3 | Sprint 3 | 2025-12-26 | 2026-01-08 | AI Engineer | Hybrid urgency logic | Pure ML urgency detection | Rule-based overrides | Improved urgency precision
4
5
6
7