## Defect_tracker
ID | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2025-12-09 | Dataset contained null email bodies | Milestone 1 | Backend Team | Data Defect | Added null removal & cleaning script | 2025-12-06 | Closed | Resolved in preprocessing
2 | 2025-12-09 | Special characters not removed from text | Milestone 1 | Backend Team | Logic Defect | Added regex text normalization | 2025-12-07 | Closed | Improved accuracy
3 | 2025-12-22 | Model misclassifying spam as request | Milestone 2 | Backend Team | Algorithm Defect | Retrained with balanced data | 2025-12-17 | Closed | Accuracy improved to 96%
4 | 2025-12-22 | API returned 500 for empty input | Milestone 2 | Backend Team | API Defect | Added validation in endpoint | 2025-12-17 | Closed | Graceful error added
5 | 2025-12-22 | API timeout on large text | Milestone 2 | Backend Team | Performance Defect | Increased timeout & optimization | 2025-12-19 | Closed | Stable now
6 | 2026-01-06 | Login accepted blank password | Milestone 3 | Frontend Team | Validation Defect | Added required field check | 2026-01-03 | Closed | UI validation added
7 | 2026-01-06 | Sidebar navigation not switching pages | Milestone 3 | Frontend Team | UI Logic Defect | Corrected session routing | 2026-01-03 | Closed | Working properly
8 | 2026-01-06 | Category shown as numeric values | Milestone 3 | Frontend Team | Display Defect | Mapped to labels | 2026-01-03 | Closed | Shows complaint/request
9 | 2026-01-06 | Badges not visible in inbox | Milestone 3 | Frontend Team | UI Defect | Added CSS badge classes | 2026-01-04 | Closed | Colors visible
10 | 2026-01-06 | Table index started from 0 | Milestone 3 | Frontend Team | Formatting Defect | Changed index +1 | 2026-01-04 | Closed | As required
11 | 2026-01-20 | Dashboard charts not updating | Milestone 4 | Frontend Team | Integration Defect | Linked session data | 2026-01-17 | Closed | Dynamic update
12 | 2026-01-20 | EC2 deployment port conflict | Milestone 4 | Backend Team | Deployment Defect | Killed old process | 2026-01-17 | Closed | App running
13 | 2026-01-20 | Streamlit not found in venv | Milestone 4 | Backend Team | Environment Defect | Activated venv & installed | 2026-01-18 | Closed | Fixed
14 | 2026-01-20 | API URL hardcoded localhost | Milestone 4 | Frontend Team | Config Defect | Updated to EC2 IP | 2026-01-18 | Closed | Live working
15 | 2026-01-20 | Script execution indentation error | Milestone 4 | Frontend Team | Syntax Defect | Corrected structure | 2026-01-19 | Closed | App stable